## RI-SEQ
RUNNING IN SEQUENCE OF RS 5 # 8ZH
DATE: 22-11-2007
NOTE:
A) | REMOVE WEAR BUSHING IF ANY
B) | MAKE UP T0RQUE OF 2E TUBING = 2250 FT-LB (OPTM.)
C) | DRIFT ALL TUBINGS WITH 2.31" RABBIT.
D) | APPLY DOPE ON PIN END ONLY.
1 | 2E PERF. CLOSED END + 2 NOS 2E PERF. TUBING ( SL.NO 60 TO 59 ).
2 | 2E BLIND TUBINGS ------------------------------------ 3 NOS (SL.NO 253 TO 251)
3 | 2E PERF.TUBINGS -------------------------------------32 NOS (SL.NO 58 TO 27)
4 | 2E BLIND TUBINGS ------------------------------------ 4 NOS (SL.NO 250 TO 247)
5 | 2E SHEAR JOINT + SINGLE
6 | 2E TUBINGS-----------------------------------------------7 NOS ( SL.NO 246 TO 240)
7 | 2E L / NIPPLE + PUP JOINT
8 | 2E X 7" PACKER + SINGLE
9 | MMG - V + SINGLE
10 | 2E TUBINGS-----------------------------------------------16 NOS ( SL.NO 239 TO 224)
11 | MMG - IV + SINGLE
12 | 2E TUBINGS-----------------------------------------------34 NOS ( SL.NO 223 TO 190)
13 | MMG - III + SINGLE
14 | 2E TUBINGS-----------------------------------------------50 NOS ( SL.NO 189 TO 140)
15 | MMG - II + SINGLE
16 | 2E TUBINGS-----------------------------------------------61 NOS ( SL.NO 139 TO 79)
17 | MMG - I + SINGLE
18 | 2E TUBINGS-----------------------------------------------32 NOS ( SL.NO 78 TO 47)
19 | 2E F/C +SSSV +F/C + SINGLE
20 | MAKE CONNECTIONS WITH C/LINE.TEST AT 4500 PSI.
21 | 2E TUBINGS-----------------------------------------------15 NOS ( SL.NO 46 TO 32)
22 | RIG UP W/LINE AND CARRY OUT DUMMY RUN WITH W/LINE
23 | INSTALL T/H AND TERMINATE C/LINE. INSTALL BPV & LOWER T/HANGER
25 | TEST T/H SEALS AT 2000 PSI. TIGHTEN ANCHOR BOLTS
26 | REMOVE BOP.CLEAN W/HEAD FLANGE.
27 | CARRY OUT W/HEAD CONNECTION AND TEST AT 4500 PSI
28 | INSTALL X -MASS TREE.TEST ADAPTER FLANGE AT 4500 PSI.
29 | REMOVE BPV.TEST X -MASS TREE VALVES AT 4500 PSI |  | 0
30 | RIG UP W/LINE .INSTALL SURGE PLUG WITH W/LINE
31 | SET PACKER .TEST PACKER AT 1000 PSI THROGH ANNULLUS KEEPING TUBING
PRESSURE 2000 PSI. BLEED OF ANNULLUS PRESSURE.
FURTHER PRESSURISETUBING TO 3000 PSI AND BLEED OFF SLOWLY.
32 | RIG UP FLOW BACK LINES TO BURNER.
33 | ACTIVATE THE WELL WITH GAS INJECTION
34 | RIG UP W/LINE .REMOVE SURGE PLUG
35 | HAND OVER THE WELL TO PLATFORM

## COMP.Diag
COMPLETION TALLY WELL NO. RS 5 # 8 Z H
RIG - TRIDENT- XII | [8 empty] | DATE - 22.11.07
PLATFORM - ICP
Sr. | DESCRIPTION |  | MAKE | SIZE | LENGTH | DEPTH | DEPTH | ANGLE | REMARKS
No. | [5 empty] | TH in M | KB in M
1 | KB |  |  |  | 17.84
2 | T / H |  | BHEL | 2E | 0.4 |  |  |  | CASING DETAILS:
3 | 3E X 2E X-OVER |  |  |  | 0.3 |  |  |  | 13 3/8" = 1400 M
4 | TUBINGS 15 NOS |  | MSL | 2E | 139.5 |  |  |  | 9 5/8" = 2123 M
5 | TUBING |  | MSL | 2E | 9.35 |  |  |  | 7" (H/T) = 2018 M
6 | FLOW COUPLING |  | PARVEEN | 2E | 1.17 | 150.72
7 | SSSV |  | OTIS | 2E | 1.52 |  |  |  | 7" W/STOCK @ 2124 M
8 | FLOW COUPLING |  | PARVEEN | 2E | 1.17
9 | TUBINGS 32 NOS |  | MSL | 2E | 296.16
10 | TUBING |  | MSL | 2E | 8.91 | 458.48
11 | MMG I |  | W/FORD | 2E | 2.58
12 | TUBINGS 61 NOS |  | MSL | 2E | 565.19
13 | TUBING |  | MSL | 2E | 9.3 | 1035.55 |  |  | -
14 | MMG II |  | W/FORD | 2E | 2.72
15 | TUBINGS 50 NOS |  | MSL | 2E | 464.59
16 | TUBING |  | MSL | 2E | 8.86 | 1511.72
17 | MMG III |  | W/FORD | 2E | 2.92
18 | TUBINGS 34 NOS |  | MSL | 2E | 313
19 | TUBING |  | MSL | 2E | 9.5 | 1837.14
20 | MMG IV |  | W/FORD | 2E | 2.94
21 | TUBING 16 NOS |  | MSL | 2E | 147.75 |  |  |  | 7" H/T @ 2018 M
22 | TUBING |  | MSL | 2E | 9.5 | 1997.33
23 | MMG-V (CV) |  | W/FORD | 2E | 2.94
24 | TUBING |  | MSL | 2E | 9.43 | 2009.7 | 2027.54 | 63 DEG
25 | 2E X 7" High angle HY PKR |  | W/FORD | 2E | 1.45
26 | PUP JOINT |  | MSL | 2E | 1.79 | 2012.94 | 2030.78 | 64 DEG
27 | L/ Nipple 2.313" WXN |  | W/FORD | 2E | 0.3
28 | TUBINGS (7 NOS) |  | MSL | 2E | 64.65
29 | TUBING |  | MSL | 2E | 8.87
30 | SHEAR JOINT |  |  | 2E | 0.25 |  | 2105
31
BELOW SHEAR JOINT (IN LATERAL- II)
2E BLIND(4 NOS) +2E PERF.(32 NOS)+2E BLIND( 3 NOS) +2E PERF(3NOS)
BLIND(2120-2140M) + PERF(2140-2440M)+BLIND(2440 - 2465M)+ PERF(2465 -2500M)
LAT-I ( 2124 M TO 2440 M)
LATERAL - I
PERF (2200-2295M) ;BLIND(2295 - 2370 M)
PERF (2370-2390M) ;BLIND(2390 - 2420 M)
| PERF (2420 - 2437M) | [7 empty] | 5" setting collar @ 2197m
WHIPSTOCK TOP @ 2124 M
GLV DESIGN :-
| SL NO. | DEPTH m | PORT | PTRO | PTRC
| GLV - I | 457 | 16/64" | 844 | 789
| GLV - II | 1029.5 | 16/64'' | 827 | 773
| GLV - III | 1501.4 | 20/64" | 834 | 748 |  | LAT-II ( 2189 M TO 2505 M)
| GLV - IV | 1838 | 20/64" | 817 | 733
| GLV - V (CV) | 2039 | 24/64" | CV | CV |  |  |  |  | MPASS PKR AT 2415 M
WITH SHOE AT 2446 M
JOB DONE:
PULL OUT OLD 3 1/2"E COMPLETION STRING WITH 7 " HYD/PACKER. PLACED CEMENT PLUG.DRILLED CEMENT
UPTO 2175M & TESTED @ 1000 PSI. SET 7" WHIPSTOCK WITH TOP AT 2124 M. CUT WINDOW. DRILLED 6" SRDH (LAT-I)
FROM 2124 M TO 2440 M, LOWERED 2 7/8 BLIND/PERF. COMBINATION KEEPING 5" SETTING COLLAR AT 2197M.
DRILLED 6" SRDH (LAT-II) FROM 2189M TO 2505M. COMPLETED THE WELL AS CTU FRIENDLY.
(FOR COMPLETE DETAIL SEE WELL DIAGRAM)